## ProjectData
Scheduled DateTime | Project Name | Overall Status | Key Progress | Risks/Blockers | Support Needed | Task No | Task Name | Task Description | ETA | Status | QA Status | Owner Name | QA Owner | Duration
2025-12-01T13:04:00+05:30 | Niotechone | OnTrack | Q & A Pages | - | - | #2276 | Q and A pages | Q and A main page create | 2 hours | Done | NA | Jalpa | NA | 2 hours
| Niotechone |  |  |  |  | #2276 | Q and A pages | Q and A - Category main page create | 20 min | Done | NA | Jalpa | NA | 30 min
| Niotechone |  |  |  |  | #2276 | Q and A pages | Q and A - details pages | 2 hours | In Progress | NA | Jalpa | NA | 1:30 hours
| Brewtopia | OnTrack | Changes/Razorpay Integration | - | - | #2667 | Brewtopia Changes - 30/09/2025 | New changes in home page and products | 2 hours | Done | NA | Darshit | NA | 2 hours
| Brewtopia |  |  |  |  | #2667 | Brewtopia Changes - 30/09/2025 | R&D about razorpay with shopify | 2 hours | Done | NA | Darshit | NA | 45 min
| Brewtopia |  |  |  |  | #2667 | Brewtopia Changes - 30/09/2025 | R&D about Domain | 30 min | In Progress | NA | Darshit | NA | 30 min
| SMGC | OnTrack | Hero Section Change | - | - | #2669 | Changes 30/09/2025 | Changes in hero section banner images | 45 min | Done | NA | Darshit | NA | 45 min
2025-11-18T15:42:00+05:30 | Alpha | OnTrack | Q & A Pages | - | - | #2235 | Q and A pages | Q and A main page create | 2 hours | Done | NA | John | NA | 2 hours
| Alpha |  |  |  |  | #2235 | Q and A pages | Q and A - Category main page create | 20 min | Done | NA | John | NA | 30 min
| Alpha |  |  |  |  | #2235 | Q and A pages | Q and A - details pages | 3 hours | In progress | NA | John | NA | 3 hours
| Pearl | OnTrack | Changes Integration | - | - | #2655 | Changes - 30/09/2025 | New changes in home page and products | 2 hours | Done | NA | Alice | NA | 2 hours
| Pearl |  |  |  |  | #2655 | Changes - 30/09/2025 | R&D about latest info | 45 min | Done | NA | Alice | NA | 45 min
| Pearl |  |  |  |  | #2656 | Changes - 30/09/2025 | R&D about Domain | 30 min | In progress | NA | Alice | NA | 30 min
2025-11-12T15:42:00+05:30 | SEO | OnTrack | 5 backlinks- Done 2 blogs Published - Done | - | - | #3032 | Off- page SEO | Generate backlinks (1)Profile submission: https://www.cake.me/me/niotechone-software-solution-pvt-ltd (2)Image Submission:https://www.imagevenue.com/ME1BWMOF (3)PDF Submission:https://www.dropbox.com/scl/fi/e9w3a9yf5f2wqt7tk4al6/Niotechone-Software-Soltuion-Pvt.-Ltd..pdf?rlkey=f3g7o7hmxxdpai4c8exu1or6w&e=1&st=25r5r9eg&dl=0 (4)Article Submission: https://telegra.ph/The-Future-of-AI-in-Healthcare-Beyond-Chatbots-and-Diagnosis-11-06 (5)web 2.0: https://niotechone.mystrikingly.com/blog/human-centered-ai-designing-systems-that-think-with-us-not-for-us | 2:50 hours | Done | NA | Shivani | NA | 2:50 hours
| SEO |  |  |  |  | #3030 | On page SEO | Published blogs (1)https://niotechone.com/blog/qa-in-the-age-of-ai-balancing-automated-tests-human-review-and-risk/ (2)https://niotechone.com/blog/practical-guide-to-cloud-cost-optimization-for-mid-market-companies/ |  | Done | NA | Kinal | NA
| SEO |  |  |  |  | #3030 | On page SEO | Schedule the blogs | 1:50 hours | Done | NA | Shivani | NA | 1:50 hours
| SEO |  |  |  |  | #3030 | R&D | check seo performance and add photos in GBP | 30 min | TODO | NA | Kinal | NA | 35 min
| SEO |  |  |  |  | #2253 | Create Content | Edit blog contents of dotnet developer roadmap | 30 min | Done | NA | Kinal | NA | 25 min
| SEO |  |  |  |  | #2253 | Create Content | prepare blog contents | 3:50 hours | On hold | NA | Kinal | NA | 3:50 hours
| SEO |  |  |  |  | #2253 | QA Sheet |  | 2 hour | In progress | NA | Kinal | NA | 2 hour
| SEO |  |  |  |  | #3087 | Prepare Blog | Prepare Blogs with check AI(use different tools) and humanize content(use different tools) with trending keywords and add External links | 2 hour | In progress | NA | Shivani | NA | 4:50 hour
2025-11-11T18:11:00+05:30 | Niotechone Website | OnTrack | Redesign of technologies page and solved bug | - | - | #3160 | New re-desine technology page | New re-desine technology page - angular page | 3:50 Hours | in progress | N/A | Nyewkesh | N/A | 4:50 Hours
| Niotechone Website |  |  |  |  | #3183 | Bug- When all blogs are ended Remove load more button | Bug- When all blogs are ended Remove load more button -Blog page | 10 Min | Done | N/A | Nyewkesh | N/A | 10 Min
| Niotechone Website |  |  |  |  | #3249 | Bug-.net devloper experinece is mismatch | Bug-.net devloper experinece is mismatch | 10 Min | Done | N/A | Nyewkesh | N/A | 10 Min
| Niotechone Website |  |  |  |  | #3182 | Bug-No categories found on this blogs | Bug-No categories found on this blogs | 10 Min | Done | N/A | Nyewkesh | N/A | 10 Min
| Niotechone Website |  |  |  |  | #3162 | Bug- Found NodeJS banner in Javascript devlopment page | Bug- Found NodeJS banner in Javascript devlopment page | 10 Min | Done | N/A | Nyewkesh | N/A | 10 Min
| Niotechone Website |  |  |  |  | #3161 | Bug-Internal redirection is not valid on this card | Bug-Internal redirection is not valid on this card | 15 Min | in progress | N/A | Nyewkesh | N/A | 15 Min
| Niotechone Website |  |  |  |  | #3158 | Bug-“Our Expertise” section display differs from previous | Bug-“Our Expertise” section display differs from previous one– About Us page [all pages where apply] | 20 Min | Done | N/A | Nyewkesh | N/A | 20 Min
| Niotechone Website |  |  |  |  | #3209 | Niotechone - Q and A shopify page(12 post) | shopify post 9 post added today | 7 hours | Done | N/A | Disha | N/A | 6:30 hours
| Ayuvita Ayurveda | OnTrack | Check for responsive | - | - | #3208 | Responsive page | Responsive home page with new sections | 2hours | Done | N/A | Darshit | N/A | 2hours
| SMGC | OnTrack | Flow execution | - | - | #3219 | Add new images | Added new images in desktop and mobile, add banner slider in contact page, add mobile image upload option in contact slider | 1:30 hours | Done | N/A | Darshit | N/A | 1:30 hours
| SMGC |  |  |  |  | - | Meeting with nikhil sir | Meeting with nikhil sir | 45 min | Done | N/A | Darshit | N/A | 45 min
| SMGC |  |  |  |  | #3215 | Product page form | add new form with image upload in products page | 2 hours | Done | N/A | Darshit | N/A | 2 hours
| SEO | OnTrack | On page- Off page SEO and Prepared Blog content | - | - | #3032 | Off- page SEO | Generate backlinks (1)profile submission:https://profiles.xero.com/people/niotechonesoftwaresolutionpvtltd (2)Image Submission:https://www.houzz.com/photos/custom-web-and-mobile-app-development-company-phvw-vp~214339141 (3)PDF Submission:https://limewire.com/d/9pbzu#cuHQZbRVmg (4)Article Submission: https://niotechone.stck.me/chapter/1383523/AI-Powered-Automation-in-Business-Transforming-Operations-for-the-Digital-Future (5)web 2.0:https://penzu.com/p/927eb2927e93838c | 2:15 min | Done | N/A | Shivani | N/A | 2:15 min
| SEO |  |  |  |  | #3030 | On page SEO | Publish blogs (1)https://niotechone.com/blog/microservices-at-scale-outsourcing-failures/ (2)https://niotechone.com/blog/global-talent-trends-2025-what-outsourcing-companies-should-know-about-developer-skills-ai/ | 2:15 min | Done | N/A | Kinal | N/A | 2:15 min
| SEO |  |  |  |  | #3030 | On page SEO | Schedule the blogs | 3:50 hours | Done | N/A | Shivani | N/A | 3:50 hours
| SEO |  |  |  |  | #3030 | R&D | check seo performance and add photos in GBP | 30 min | Done | N/A | Shivani | N/A | 35 min
| SEO |  |  |  |  | #2253 | Create Content | prepare blog contents | 30 min | In progress | N/A | Kinal | N/A | 30 min
| SEO |  |  |  |  | - | Friday Sheet | Update Friday Sheet | 1 hour | Done | N/A | Kinal | N/A | 1 hour
| SEO |  |  |  |  | #3087 | Prepare Blog | Prepare Blogs with check AI(use different tools) and humanize content(use different tools) with trending keywords and add External links | 4:50 hour | In progress | N/A | Shivani | N/A | 4:50 hour
2025-11-20T15:42:00+05:30 | Healer | OnTrack | Q & A Pages | - | - | #2276 | Q and A pages | Q and A main page create | 2 hours | Done | NA | John | NA | 2 hours
| Healer |  |  |  |  | #2276 | Q and A pages | Q and A - Category main page create | 20 min | Done | NA | John | NA | 30 min
| Healer |  |  |  |  | #2276 | Q and A pages | Q and A - details pages | 3 hours | In Progress | NA | John | NA | 3 hours
| Techie | OnTrack | Changes Integration | - | - | #2667 | Changes - 30/09/2025 | New changes in home page and products | 2 hours | Done | NA | Alice | NA | 2 hours
| Techie |  |  |  |  | #2667 | Changes - 30/09/2025 | R&D about latest info | 45 min | Done | NA | Alice | NA | 45 min
| Techie |  |  |  |  | #2668 | Changes - 30/09/2025 | R&D about Domain | 30 min | In Progress | NA | Alice | NA | 30 min
2025-11-24T18:40:00+05:30 | Designing | 🟢 On Track | Canada Site / Blog |  |  | #3387 | New niotechone blog img | New niotechone blog img | 3 hours | On hold | NA | Chirag | NA | -
| Designing |  |  |  |  | #3342 | Niotechone canada site | Services sections created and R&D for other services. (service page done and expertise page rnd continue) |  | In Progress | NA | Chirag | NA | 6:15 hours
| Designing |  |  |  |  | - | Niotechone canada site understanding | All sections understanding with prototype (Nyewkesh & janvi ma'am). | 25 min | Done | NA | Chirag | NA | 25 min
| FTA | 🔴 Delayed | 1553 Testing / SP optimized / SQL Refactoring |  |  | #1607 | 1553 | Testing 1553 and note down the performance metrics | - | In Progress | N/A | Raj | NA | 30 min
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring | - | In Progress | N/A | Raj | NA | 2 hour
| FTA |  |  |  |  | - | - | Replace optimized SP to Dev and Staging - Sachin | 1:5 hours | Done | N/A | Raj | NA | 1:30 hours
| FTA |  |  |  |  | - | - | Revert changes of optimized SP to Dev and Staging - Sachin | 30 min | Done | N/A | Raj | NA | 30 min
| TSC | 🔴 Delayed | 205 Bug / SQL Refactoring | Lack in priority set up |  | #3328 | 205 | RFICL013 - Exceptions Report cannot be delivered to e-mail - Find Root cause | 1 hour | In Progress | N/A | Raj | NA | 1 hour
| TSC |  |  |  |  | - | - | Working on code and SQL refactoring | - | In Progress | N/A | Dhaval | NA | 4:5 hours
| Others | 🟢 On Track | DSM |  |  | - | - | Internal DSM | 30 min | Done | N/A | Raj / Dhaval | NA | 30 min
| Others |  |  |  |  | - | - | Internal Meeting for RDC session | 30 min | Done | N/A | Raj / Dhaval | NA | 30 min
| Najm-Claim-Experience | 🟢 On Track | Configuration Setting / KT Session |  |  | #3485 | Configuration setting | Set the configurations from appsettings for HF job into the JobSettings database table | 2:5 hours | Done | NA | Janvi | NA | 1 hours
| Najm-Claim-Experience |  |  |  |  | #3466 | KT Session | KT Session for Claim Experience, Vehicle Insurance Inquiry and ELM Integration | 1:5 hours | Done | NA | Hardik | NA | 1:5 hours
| Najm-Claim-Experience | 🟢 On Track | Unit Testing |  |  | #3416 | Unit Testing | Solve Errors in Unit testing for Claim Expereince proj | 1:5 hours | Done | NA | Hardik | NA | 1:5 hours
| Najm-ELM Integration | 🟢 On Track | Meeting |  |  | NA | Meeting | Common DSM Meeting – Parth Talaviya 24/11/2025 | 30 min | Done | NA | Team | NA | 30 min
| Najm-ELM Integration | 🟢 On Track | Meeting |  |  | NA | Meeting | Integration DSM Meeting Parth Talaviya 24/11/2025 | 30 min | Done | NA | Team | NA | 30 min
| Najm-Claim-Experience | 🟢 On Track | Code Debug |  |  | NA | Code Debug | Code Debugging for Claim Experience Project | 5 hours | In Progress | NA | Janvi | NA | 2 hours
| Kentico - Raymour and Flaningan | 🔴 Delayed | PR Review / Code Update | Lack of knowledge |  | #35630 | PR review | Internal call with abhishek for PR reviewing | 2 hours | Done | NA | Nutan & Chirag | NA | 2 hours
| Kentico - Raymour and Flaningan |  |  |  |  | - | Update the code as required | Code updatation and testing locally as discussed with abhishek | 1 hour | Done | NA | Nutan & Chirag | NA | 1 hour
| Kentico - Raymour and Flaningan |  |  |  |  | #61144 | Product Card aligning misaligned content | Created a new branch for new ticket#61144 and started working on that | 2 hours | In Progress | NA | Nutan & Chirag | NA | 2 hours
| Kentico - Raymour and Flaningan |  |  |  |  | - |  | Some of work is done and for some of work we need to discuss with team in meeting | 3 hour | In Progress | NA | Nutan & Chirag | NA | 3 hours
2025-11-25T18:38:00+05:30 | Designing | 🟢 On Track | Blog/ Canada Site |  |  | #3387 | New niotechone blog img | New niotechone blog img | 3 hours | Done | NA | Chirag | NA | 45 mins
| Designing |  |  |  |  | #3342 | Niotechone canada site | Niotechone canada site | - | In Progress | NA | Chirag | NA | 5:30 hours
| Designing |  |  |  |  | - | The autist | Changes in hero section and background / Font | - | Done | NA | Chirag | NA | 15 mins
| Najm-Vehicle-Insurance-Inquiry | 🟢 On Track | Code debug |  |  | NA | Code debug | Code debug | 1 hour | Done | NA | Janvi | NA | 1 hour
| Najm-Claim-Experience | 🟢 On Track | Code debug |  |  | NA | Code debug | Code debug | 2:5 hours | Done | NA | Janvi | NA | 2:5 hours
| Najm-Claim-Experience | 🟢 On Track | Configuration setting |  |  | #3485 | Configuration setting | Updated the configuration settings for the HF job, moving them from appsettings to the JobSettings database table, based on Sanbaran's suggestion | 2 hours | In progress | NA | Hardik | NA | 2 hours | Created the branch for these changes and Created PR for the same, need to check on UAT after deployment
| FTA | 🔴 Delayed | 1553 Testing / SQL Refactoring |  |  | #1607 | 1553 | Testing 1553 and note down the performance metrics | 1 hours | In progress | NA | Raj | N/A | 1 hours
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring | 2:5 hour | In progress | NA | Raj | N/A | 2:5 hour
| TSC | 🔴 Delayed | 205 Issue / Fixing an issue | Divyesh Account log in issue |  | #3328 | 205 | RFICL013 - Exceptions Report cannot be delivered to e-mail - Find Root cause | 2 hours | In progress | NA | Raj | N/A | 2 hours
| TSC |  |  |  |  | - |  | Work on fix an issue to start project with Kinjal account (TSC-TSW & FTA) | 2 hours | Done | NA | Raj | N/A | 2 hours
| TSC |  |  |  |  | - |  | Work on fix an issue to start project with Vaibhav account (TSC-TSW & FTA) | - | Failed | NA | Raj | N/A | -
| TSC |  |  |  |  | - |  | Working on code and SQL refactoring | 6 hours | In progress | NA | Dhaval | N/A | 6 hours
| Kentico (Raymour and Flaningan) | 🔴 Delayed | Alignment / Minor changes |  |  | 61164 | Product Card aligning misaligned content | As discussed with team in office hours removed the current logic for empty block | - | Done | NA | Nutan & Chirag | NA | 2 Hour
| Kentico (Raymour and Flaningan) |  |  |  |  | - | Product Card aligning misaligned content | Corrected "size" & "Color selection" as per discussion on Office hours with team and checked that AlignItemsInOrder function calls but we need to add a empty block and tested working as expected. | - | Done | NA | Nutan & Chirag | NA | 3 Hour
| Kentico (Raymour and Flaningan) |  |  |  |  | - | Product Card aligning misaligned content | Working on alignment setting for "starting at" content | - | InProgress | NA | Nutan & Chirag | NA | 3 Hour
2025-11-26T18:35:00+05:30 | TSC | 🟢 On Track | 205 |  |  | #3328 | 205 | RFICL013 - Exceptions Report cannot be delivered to e-mail - Find Root cause | 2 hours | Done | Pending | Raj | Parth | 2 hours
| FTA | 🟢 On Track | 1649/1650/1553 Testing |  |  | #3586 | 1649 | Daniela - Large Import File Testing - No build part - invalid Vendor | 3 hours | Done | Pending | Dhaval | Parth | 2 hours
| FTA |  |  |  |  | #3588 | 1650 | Investigate / Update - Upload Parts to Certificate - Error Message for Missing Part/SKU Number | 3 hours | Done | Pending | Dhaval | Parth | 3:30 hours
| FTA |  |  |  |  | - | - | Include Improter Name and Importer code in the files which we sent to Vienna | 2 hours | Done | NA | Raj | NA | 2:30 hours
| FTA |  |  |  |  | #1607 | 1553 | Testing 1553 and note down the performance metrics | - | In progress | NA | Raj | NA | 1 hours
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring For Shipment API | 3 hours | Pending | NA | Dhaval | NA | -
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring For TSB | 1 hours | Pending | NA | Raj | NA | 30 min
| FTA | 🟢 On Track | Working on code and SQL refactoring For TSB |  |  | - | - | Working on code and SQL refactoring For TaskSchedular | - | In progress | NA | Hardik | NA | 2:30 hours
| Najm-ELM Integration | 🟢 On Track | Configuration setting |  |  | #3591 | Configuration setting | Update the part where we get the CronExpression value from the appsettings file not from the DB | 3 Hours | Done | NA | Janvi | NA | 3 Hours
| Najm-ELM Integration |  |  |  |  | NA | Meeting | Common DSM Meeting – Parth Talaviya 26/11/2025 | 30 mins | Done | NA | Hardik / Janvi | NA | 30 mins
| Najm-ELM Integration |  |  |  |  | NA | Meeting | Integration DSM Meeting Parth Talaviya 26/11/2025 | 30 mins | Done | NA | Hardik / Janvi | NA | 30 mins
| Kentico - Raymour and Flaningan | 🔴 Delayed | PR creation / Changes |  |  | #30536 | Ticket Updation and Information | Updated all the required comments on ticket and informed to team in office hours | 1 Hour | Done | NA | Nutan & Chirag | NA | 1 Hour
| Kentico - Raymour and Flaningan |  |  |  |  | - | Veify changes in dev environment | Verified all the filter reseting changes | 30 Min | Done | NA | Nutan & Chirag | NA | 30 Min
| Kentico - Raymour and Flaningan |  |  |  |  | - | Draft PR Creation for UAT | Created a draft PR for the UAT | 15 Min | Done | NA | Nutan & Chirag | NA | 15 Min
| Kentico - Raymour and Flaningan |  |  |  |  | #61164 | Mail formation and sending | Create mail formation and sent it to Rinku Jain | 1:15 hours | Done | NA | Nutan & Chirag | NA | 1:15 hours
| Kentico - Raymour and Flaningan |  |  |  |  | - | Product Card aligning misaligned content | Updated business logic for "Size" and "Color selection" as per new scenario and checked it in local which is working fine | 4 hour | Done | NA | Nutan & Chirag | NA | 4 hour
| Kentico - Raymour and Flaningan |  |  |  |  | - | Ticket updation | Updated ticket comments for this changes | 20 Min | Done | NA | Nutan & Chirag | NA | 20 Min
| Kentico - Raymour and Flaningan |  |  |  |  | - | Get the look block | Started working on Get the look block | 40 Min | Done | NA | Nutan & Chirag | NA | 40 Min
2025-11-27T18:48:00+05:30 | Dubai-police | 🟢 On Track | New requirement for Convoytable |  |  | #3671 | Dubai-police convoy | Add new requirement for conveyPath table and StreetNameId | 6 hours | Done | NA | Nutan | NA | 6 hours
| Kentico - Raymour and Flaningan | 🟢 On Track | Alignment issue fixed / Changes |  |  | #61164 | Get the look block Added | Added the "Get look block" locally and reviewed it | 30 Min | Done | NA | Nutan & Chirag | NA | 30 Min
| Kentico - Raymour and Flaningan |  |  |  |  | - | Get the look block code correction | Found the root area of work and updated the code and fixed the alignment of "Get the look" block | 4 Hour | Done | NA | Nutan & Chirag | NA | 4 Hour
| Kentico - Raymour and Flaningan |  |  |  |  | - | Get the look block testing | Tested this on local and working as expected | 1 Hours | Done | NA | Nutan & Chirag | NA | 1 Hours
| Kentico - Raymour and Flaningan |  |  |  |  | - | Remove unnecessary code | Removed unused and commented code from actual logic and optimized the code . | 30 Min | Done | NA | Nutan & Chirag | NA | 30 Min
| Kentico - Raymour and Flaningan |  |  |  |  | - | Dynamic content | updated static value to dynamic from all the area of work for "Size", "Price", "Color-selection", "Starting at", "Gert the look" and tested which is working as expected | 2 Hours | Done | NA | Nutan & Chirag | NA | 2 Hours
| TSC | 🟢 On Track | Check Complete TSC on staging |  |  | - | Check Complete TSC on staging to be ready for production | Check Complete TSC on staging to be ready for production | 2 hours | Done | NA | Raj | NA | 2 hours
| ShipmentAPI | 🟢 On Track | SQL refactoring For Shipment API |  |  | - | Working on code and SQL refactoring For Shipment API | Working on code and SQL refactoring For Shipment API | 5 hours | In progress | NA | Dhaval | NA | 5:5 hours
| TM | 🟢 On Track | TM-Part ODG, as per Wendi comment |  |  | - | TM-Part ODG, as per Wendi comment | TM-Part ODG, as per Wendi comment | 2 hours | In progress | NA | Raj | NA | 3 hours
| FTA | 🟢 On Track | 1553 Testing / SQL refactoring For TSB and Shipment API |  |  | #1607 | 1553 | Testing 1553 and note down the performance metrics | - | In progress | NA | Raj | NA | 2 hours
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring For TSB |  | In progress | NA | Raj | NA | 1:5 hours
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring For Shipment API |  | In progress | NA | Dhaval | NA | 1 hours
| FTA |  |  |  |  | - | - | Working on code and SQL refactoring For TSB | 4 hours | Pending | NA | Raj | NA | -
| TSB | 🟢 On Track | 1650 |  |  | #3588 | 1650 | Investigate / Update - Upload Parts to Certificate - Error Message for Missing Part/SKU Number | - | Hold | NA | Dhaval | NA | -
| TSB |  |  |  |  | - | - | Check Email from Ibrahim and update accordingly | 30 min | Pending | NA | Raj | NA | -
TSB
TSB
TSB
2025-11-28T18:39:00+05:30 | Shipment API | 🟢 On Track | SQL refactoring For Shipment API |  |  | - | - | Working on code and SQL refactoring For Shipment API |  | Done | NA | Dhaval | NA | 1 hour
| TM | 🔴 Delayed | TM-Part ODG, as per Wendi comment | Took more time than ETA |  | #3724 | 2534 | TM-Part ODG, as per Wendi comment | 3 hours | Done | NA | Raj | NA | 6:5 hours
| FTA | 🔴 Delayed | 1650 / 1553 testing |  |  | #3588 | 1650 | Investigate / Update - Upload Parts to Certificate - Error Message for Missing Part/SKU Number | - | Hold | NA | Dhaval | NA | -
| FTA |  |  |  |  | #1607 | 1553 | Testing 1553 and note down the performance metrics | 1 hour | In Progress | Pending | Raj | Parth | -
| TSB | 🟢 On Track | SQL refactoring For TSB |  |  | - | - | Working on code and SQL refactoring For TSB | 4 hours | Pending | NA | Raj | NA | -
| TSC | 🟢 On Track | 207/ SQL refactoring For TSB / Footprint status check |  |  | - | - | Working on code and SQL refactoring For TSC | 5:5 hours | In Progress | NA | Dhaval | NA | 2 hours
| TSC |  |  |  |  | - | 207 | Need to investigate dual entry of Exception | 1:5 hours | Done | Parth | Dhaval | Parth | 3 hours
| TSC |  |  |  |  | - | - | Check Email from Ibrahim and update accordingly | 30 min | Pending | NA | Raj | NA | -
| TSC |  |  |  |  | - | - | Foot print Status | 30 min | Done | NA | Raj | NA | 30 min
| Najm-ELM Integration | 🟢 On Track | UAT Testing / Sonar findings |  |  | NA | UAT testing | Testing the configuration changes for getting CronExpression value from the appsettings file not from the DB | 1 Hour | Done | NA | Janvi | NA | 1 Hour
| Najm-ELM Integration |  |  |  |  | NA | CodeReview Branch | Create CodeReview branch for all 3 projects and follow the process for peer review for 3 all prjects | 1 Hour | Done | NA | Hardik | NA | 1 Hour | We have send message in Common once review by other dev based on comment we need to update the code
| Najm-ELM Integration |  |  |  |  | NA | Sonar Findings | Check for the Sonar findings for each project and prepare list for all 3 projects | ETA after receiving inputs | In Progress | NA | Hardik | NA |  | We have send message in Common once get input then we will work on that
| Kentico - Raymour and Flaningan | 🟢 On Track | Added the "Get look block" / Local testing / Remove unnecessary code |  |  | #61164 | Get the look block Added | Internal call with Ankit and Added the "Get look block" locally and reviewed it | 2 hours | Done | NA | Nutan & Chirag | NA | 2 hours
| Kentico - Raymour and Flaningan |  |  |  |  | - | Get the look block code correction | Logic and code updated with proper implementation and tested in local working as expected | 4 hours | Done | NA | Nutan & Chirag | NA | 4 hours
| Kentico - Raymour and Flaningan |  |  |  |  | - | Remove unnecessary code | Card showing logic for per row is updated and tested it locally working as expected | 2 hours | Done | NA | Nutan & Chirag | NA | 2 hours

## QA
Project Name | Task No | Task Name | QA Status | Owner Name | QA name | Bug id | Reopen bug | Success Criteria | Duration
Alpha | #2235 | Bug : FAQ section UI displays unnecessary blank space on "Service Pages" | ReAssign to dev | John | Parth | https://niotechone.in/index.php/tasks/view/3338 | Yes | NO | 10 min
Alpha | #2235 | Bug : FAQ section UI displays unnecessary blank space on "Service Pages" | ReAssign to dev | John | Parth | https://niotechone.in/index.php/tasks/view/3339 | - | -
Pearl | #2655 | Bug-Remove/Close Internal redirection Service page |  | Alice | Aditya | https://niotechone.in/index.php/tasks/view/3340 | No |  | 30 min
Pearl | #2656 | Bug-Remove/Close Internal redirection Service page |  | Alice | Aditya | https://niotechone.in/index.php/tasks/view/3341 | Yes |  | 30 min